## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | As a customer, I want to send a support message so that the system can understand my request. | Must Have | Customer Simulator | Sinjini | 3- Completed
1 | 1 | US-02 | As a support system, I want to detect customer intent so that the response workflow can use the correct issue category. | Must Have | Conversation input | Krishna Kumar | 3- Completed
1 | 1 | US-03 | As a support system, I want to classify customer sentiment as positive, neutral, or negative so that customer tone is visible. | Must Have | Intent analysis | Sneha | 3- Completed
1 | 1 | US-04 | As a support system, I want to classify customer emotion such as happy, confused, worried, frustrated, angry, or satisfied. | Should Have | Sentiment analysis | Sneha | 3- Completed
2 | 2 | US-05 | As a support system, I want to calculate a 0–10 frustration score from customer language and repeated complaints. | Must Have | Intent/emotion modules | Sinjini | 3- Completed
2 | 2 | US-06 | As a support system, I want to detect escalation risk as Low, Medium, or High. | Must Have | Frustration score | Sinjini | 3- Completed
2 | 2 | US-07 | As a support system, I want to track satisfaction as Improving, Declining, or Stable across conversation history. | Must Have | Sentiment history | Vardhan | 3- Completed
2 | 2 | US-08 | As a support system, I want to maintain conversation history so that follow-up messages are interpreted using previous context. | Must Have | Conversation state | Vardhan | 3- Completed
3 | 3 | US-09 | As a customer, I want short follow-up messages such as "any update?" to retain the original issue context. | Should Have | Conversation history | Krishna Kumar | 3- Completed
3 | 3 | US-10 | As a support system, I want confidence values bounded between 0 and 1 so analysis remains structured and reliable. | Should Have | Classification modules | Sneha | 3- Completed
3 | 3 | US-11 | As a support system, I want structured analysis returned for every customer message. | Must Have | Analysis modules | Krishna Kumar | 3- Completed
3 | 3 | US-12 | As a support system, I want the Customer Simulator to trigger analysis for every generated customer turn. | Must Have | Customer Simulator | Vardhan | 3- Completed
4 | 4 | US-13 | As a developer, I want an API endpoint for message analysis so the analysis agent can be consumed by other applications. | Must Have | Analysis engine | Krishna Kumar | 3- Completed
4 | 4 | US-14 | As a developer, I want RAG retrieval integrated with the support response flow so answers are grounded in support documents. | Must Have | Vector store / knowledge base | Harshitha | 3- Completed
4 | 4 | US-15 | As a developer, I want the bundled support PDFs to be indexed automatically at startup when the knowledge base is empty. | Must Have | RAG pipeline | Harshitha | 3- Completed
4 | 4 | US-16 | As a support system, I want generated responses to use relevant support-document context where available. | Should Have | RAG retrieval | Harshitha | 3- Completed
5 | 5 | US-17 | As a developer, I want at least 20 customer scenarios tested across intent, sentiment, emotion, frustration, and escalation. | Must Have | Analysis modules | Sinjini | 3- Completed
5 | 5 | US-18 | As a developer, I want multi-turn conversation tests so context inheritance and satisfaction trend are verified. | Must Have | Conversation history | Vardhan | 3- Completed
5 | 5 | US-19 | As a developer, I want technical documentation describing architecture, API, testing, and demonstration flow. | Must Have | Completed implementation | Krishna Kumar | 3- Completed
5 | 5 | US-20 | As a user, I want a working Streamlit demonstration that shows the AI support workflow end to end. | Must Have | FastAPI + RAG + analysis | Harshitha | 3- Completed
6 | 6 | US-21 | As a support agent, I want real-time context-aware response suggestions evaluated for tone, clarity, empathy, and professionalism along with actionable communication tips. | Must Have | Intent & Sentiment Analysis Agent, RAG Pipeline | Krishna Kumar | 3- Completed
6 | 6 | US-22 | As a supervisor, I want continuous escalation risk monitoring that scores conversations (0–100) and classifies them into Low, Medium, High, and Critical risk tiers with explicit reasoning. | Must Have | Frustration & Sentiment history | Sinjini | 3- Completed
6 | 6 | US-23 | As a support agent, I want configurable threshold alerts with overlay banners and recommended corrective actions (tone shift, empathy pivot, supervisor transfer). | Must Have | US-22 Risk Engine | Sneha | 3- Completed
6 | 6 | US-24 | As a system engineer, I want the Coaching & Escalation Agents integrated into the multi-agent pipeline so metrics recalculate on every customer message turn. | Must Have | US-21, US-22, FastAPI / Streamlit UI | Harshitha | 3- Completed
7 | 7 | US-25 | As a support agent, I want a three-panel Live Support Console so that I can manage conversations, coaching, and knowledge recommendations in one interface. | Must Have | Existing support analysis pipeline | Krishna Kumar | 2- In Progress
7 | 7 | US-26 | As a support agent, I want real-time coaching suggestions and communication tips after each customer message so that I can improve tone, empathy, clarity, and professionalism. | Must Have | US-25, Response Suggestion Agent | Krishna Kumar | 2- In Progress
7 | 7 | US-27 | As a support agent, I want relevant FAQs, support articles, policies, and troubleshooting steps for the current conversation context. | Must Have | US-25, RAG knowledge base | Harshitha | 2- In Progress
7 | 7 | US-28 | As a support agent, I want Manual Mode to analyze each customer message and maintain the complete conversation state across turns. | Must Have | US-25, analysis agents | Vardhan | 2- In Progress
7 | 7 | US-29 | As a support agent, I want to upload and replay recorded conversation transcripts so that previous conversations can be analyzed. | Must Have | US-25, transcript parser | Sinjini | 2- In Progress
7 | 7 | US-30 | As a support agent, I want Next, Previous, Play/Pause, and Restart controls during replay so that I can inspect conversations message by message. | Must Have | US-29 | Vardhan | 2- In Progress
7 | 7 | US-31 | As a support agent, I want escalation-risk progression and an overall replay summary so that I can understand how the conversation developed. | Must Have | US-29, Escalation Risk Agent | Sinjini | 2- In Progress
7 | 7 | US-32 | As a developer, I want test cases covering Manual Mode, Replay Mode, message analysis, coaching, knowledge recommendations, and summaries. | Must Have | US-28, US-30, US-31 | Sneha | 1- To Do

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[6 empty] | 320 | 28 | 65 | 47 | 12 | 30 | 18 | 12 | 30 | 18 | 12 | 30 | 18 | 0 | 0
SPRINT 1 BACKLOG
US-01 | 1 | Define customer-message input flow and validation | Sinjini | Planning | 3- Completed | 2 | Day 1: 2
US-01 | 2 | Connect customer message to support workflow | Sinjini | Coding | 3- Completed | 5 | Day 2: 5
US-01 | 3 | Test normal, empty, and follow-up customer inputs | Sinjini | Testing | 3- Completed | 3 | Day 3: 3
US-02 | 4 | Define intent categories and context rules | Krishna Kumar | Planning | 3- Completed | 2 | Day 4: 2
US-02 | 5 | Implement history-aware intent classification | Krishna Kumar | Coding | 3- Completed | 5 | Day 5: 5
US-02 | 6 | Test refund, cancellation, delivery, payment, account and complaint intents | Krishna Kumar | Testing | 3- Completed | 3 | Day 6: 3
US-03 | 7 | Define Positive/Neutral/Negative sentiment rules | Sneha | Planning | 3- Completed | 2 | Day 7: 2
US-03 | 8 | Implement sentiment classifier | Sneha | Coding | 3- Completed | 5 | Day 8: 5
US-03 | 9 | Test positive, neutral and negative messages | Sneha | Testing | 3- Completed | 3 | Day 9: 3
US-04 | 10 | Define emotion labels and indicators | Vardhan | Planning | 3- Completed | 2 | Day 10: 2
US-04 | 11 | Implement emotion classification | Vardhan | Coding | 3- Completed | 5 | Day 11: 5
US-04 | 12 | Test happy, confused, worried, frustrated, angry and satisfied cases | Vardhan | Testing | 3- Completed | 3 | Day 12: 3
SPRINT 2 BACKLOG
US-05 | 13 | Define 0–10 frustration scoring factors | Sneha | Planning | 3- Completed | 2 | Day 1: 2
US-05 | 14 | Implement language, repetition and escalation scoring | Sneha | Coding | 3- Completed | 5 | Day 2: 5
US-05 | 15 | Validate low, medium and high frustration messages | Sneha | Testing | 3- Completed | 3 | Day 3: 3
US-06 | 16 | Define escalation thresholds | Sinjini | Planning | 3- Completed | 2 | Day 4: 2
US-06 | 17 | Implement escalation-risk detection | Sinjini | Coding | 3- Completed | 5 | Day 5: 5
US-06 | 18 | Test urgent, legal-threat and normal conversations | Sinjini | Testing | 3- Completed | 3 | Day 6: 3
US-07 | 19 | Define satisfaction trend rules | Vardhan | Planning | 3- Completed | 2 | Day 7: 2
US-07 | 20 | Implement Improving/Declining/Stable tracker | Vardhan | Coding | 3- Completed | 5 | Day 8: 5
US-07 | 21 | Test multi-turn sentiment changes | Harshitha | Testing | 3- Completed | 3 | Day 9: 3
US-08 | 22 | Define conversation-history structure | Harshitha | Planning | 3- Completed | 2 | Day 10: 2
US-08 | 23 | Store and pass prior customer turns into analysis | Krishna Kumar | Coding | 3- Completed | 5 | Day 11: 5
US-08 | 24 | Test contextual analysis across multiple turns | Krishna Kumar | Testing | 3- Completed | 3 | Day 12: 3
SPRINT 3 BACKLOG
US-09 | 25 | Identify contextual follow-up patterns | Sinjini | Planning | 3- Completed | 2 | Day 1: 2
US-09 | 26 | Implement intent inheritance from prior customer turn | Sinjini | Coding | 3- Completed | 5 | Day 2: 5
US-09 | 27 | Test "any update", "still waiting" and "same issue" cases | Sinjini | Testing | 3- Completed | 3 | Day 3: 3
US-10 | 28 | Define confidence calculation and bounds | Sneha | Planning | 3- Completed | 2 | Day 4: 2
US-10 | 29 | Implement 0–1 confidence normalization | Sneha | Coding | 3- Completed | 5 | Day 5: 5
US-10 | 30 | Test edge cases and low-confidence inputs | Sneha | Testing | 3- Completed | 3 | Day 6: 3
US-11 | 31 | Define structured analysis response schema | Krishna Kumar | Planning | 3- Completed | 2 | Day 7: 2
US-11 | 32 | Return intent, emotion, sentiment, frustration, trend, risk and confidence | Krishna Kumar | Coding | 3- Completed | 5 | Day 8: 5
US-11 | 33 | Validate schema for every analyzed message | Krishna Kumar | Testing | 3- Completed | 3 | Day 9: 3
US-12 | 34 | Hook analysis into simulator customer-turn generation | Vardhan | Integration | 3- Completed | 2 | Day 10: 2
US-12 | 35 | Save analysis with simulator conversation history | Vardhan | Coding | 3- Completed | 5 | Day 11: 5
US-12 | 36 | Run multi-turn simulator demonstration | Vardhan | Testing | 3- Completed | 3 | Day 12: 3
SPRINT 4 BACKLOG
US-13 | 37 | Define API request and response contract | Krishna Kumar | Planning | 3- Completed | 2 | Day 1: 2
US-13 | 38 | Implement analysis endpoint in FastAPI | Krishna Kumar | Coding | 3- Completed | 5 | Day 2: 5
US-13 | 39 | Test valid and invalid requests | Krishna Kumar | Testing | 3- Completed | 3 | Day 3: 3
US-14 | 40 | Connect retrieval to support response generation | Harshitha | Integration | 3- Completed | 2 | Day 4: 2
US-14 | 41 | Use retrieved support-document context for grounded responses | Harshitha | Coding | 3- Completed | 5 | Day 5: 5
US-14 | 42 | Test relevant and irrelevant knowledge queries | Harshitha | Testing | 3- Completed | 3 | Day 6: 3
US-15 | 43 | Detect empty Chroma knowledge base at startup | Harshitha | Planning | 3- Completed | 2 | Day 7: 2
US-15 | 44 | Load, clean, chunk and index bundled support PDFs | Harshitha | Coding | 3- Completed | 5 | Day 8: 5
US-15 | 45 | Verify retrieval returns indexed support content | Harshitha | Testing | 3- Completed | 3 | Day 9: 3
US-16 | 46 | Add document metadata to retrieved context | Harshitha | Integration | 3- Completed | 2 | Day 10: 2
US-16 | 47 | Pass grounded context into answer generation | Harshitha | Coding | 3- Completed | 5 | Day 11: 5
US-16 | 48 | Test refund, payment and account support questions | Harshitha | Testing | 3- Completed | 3 | Day 12: 3
SPRINT 5 BACKLOG
US-17 | 49 | Prepare 20+ customer scenario test cases | Sinjini | Planning | 3- Completed | 2 | Day 1: 2
US-17 | 50 | Implement assertions for analysis outputs | Sinjini | Coding | 3- Completed | 5 | Day 2: 5
US-17 | 51 | Run full Task 4 scenario test suite | Sinjini | Testing | 3- Completed | 3 | Day 3: 3
US-18 | 52 | Create multi-turn context test conversations | Vardhan | Planning | 3- Completed | 2 | Day 4: 2
US-18 | 53 | Validate follow-up intent and satisfaction trend | Vardhan | Coding | 3- Completed | 5 | Day 5: 5
US-18 | 54 | Run regression tests for context handling | Vardhan | Testing | 3- Completed | 3 | Day 6: 3
US-19 | 55 | Document architecture and components | Krishna Kumar | Documentation | 3- Completed | 2 | Day 7: 2
US-19 | 56 | Document API, setup, RAG flow and testing | Krishna Kumar | Documentation | 3- Completed | 5 | Day 8: 5
US-19 | 57 | Review documentation against Task 4 deliverables | Krishna Kumar | Testing | 3- Completed | 3 | Day 9: 3
US-20 | 58 | Prepare FastAPI and Streamlit demo environment | Harshitha | Integration | 3- Completed | 2 | Day 10: 2
US-20 | 59 | Demonstrate message → analysis → grounded response flow | Harshitha | Coding | 3- Completed | 5 | Day 11: 5
US-20 | 60 | Run final end-to-end demo and fix issues | Harshitha | Testing | 3- Completed | 3 | Day 12: 3
SPRINT 6 BACKLOG
US-21 | 61 | Define evaluation metrics for empathy, tone, clarity, and coaching rubric | Krishna Kumar | Planning | 3- Completed | 2 | Day 1: 2
US-21 | 62 | Implement Response Suggestion Agent using context history, sentiment, & RAG | Krishna Kumar | Coding | 3- Completed | 5 | Day 2: 5
US-21 | 63 | Unit test suggestion engine and actionable coaching feedback generator | Krishna Kumar | Testing | 3- Completed | 3 | Day 3: 3
US-22 | 64 | Formulate escalation scoring rules (complaints, supervisor requests, sentiment) | Sinjini | Planning | 3- Completed | 2 | Day 4: 2
US-22 | 65 | Implement Escalation Risk Agent (Low, Medium, High, Critical) with reasoning | Sinjini | Coding | 3- Completed | 5 | Day 5: 5
US-22 | 66 | Benchmark escalation scoring against multi-turn conflict conversations | Sinjini | Testing | 3- Completed | 3 | Day 6: 3
US-23 | 67 | Establish alert threshold triggers and corrective intervention recommendations | Sneha | Planning | 3- Completed | 2 | Day 7: 2
US-23 | 68 | Build front-end alert banner overlay and remediation action selector | Sneha | Coding | 3- Completed | 5 | Day 8: 5
US-23 | 69 | Test threshold trigger accuracy and dynamic UI alert dismissal | Sneha | Testing | 3- Completed | 3 | Day 9: 3
US-24 | 70 | Design agent orchestration pipeline for real-time per-message execution | Harshitha | Integration | 3- Completed | 2 | Day 10: 2
US-24 | 71 | Integrate coaching & escalation modules with Intent, Sentiment, and RAG agents | Harshitha | Coding | 3- Completed | 5 | Day 11: 5
US-24 | 72 | Execute end-to-end integration and latency stress testing | Harshitha | Testing | 3- Completed | 3 | Day 12: 3
SPRINT 7 BACKLOG
US-25 | 73 | Design three-panel Live Support Console layout and conversation flow | Sinjini | Planning | 2- In Progress | 2 | Day 1: 2
US-25 | 74 | Implement conversation window with chronological messages and customer analysis indicators | Sinjini | Coding | 2- In Progress | 5 | Day 2: 5
US-25 | 75 | Test conversation history, input handling, and three-panel UI rendering | Krishna Kumar | Testing | 1- To Do | 3 | Day 3: 3
US-26 | 76 | Define coaching output for tone, empathy, clarity, and professionalism | Krishna Kumar | Planning | 2- In Progress | 2 | Day 1: 2
US-26 | 77 | Integrate real-time suggested responses, coaching tips, and escalation warnings | Krishna Kumar | Coding | 2- In Progress | 5 | Day 2: 5
US-26 | 78 | Test coaching refresh after each conversation exchange | Krishna Kumar | Testing | 1- To Do | 3 | Day 3: 3
US-27 | 79 | Define knowledge recommendation display and context retrieval flow | Harshitha | Planning | 2- In Progress | 2 | Day 1: 2
US-27 | 80 | Integrate FAQs, support articles, policies, and troubleshooting recommendations | Harshitha | Coding | 2- In Progress | 5 | Day 2: 5
US-27 | 81 | Test recommendation refresh and knowledge-content viewing | Harshitha | Testing | 1- To Do | 3 | Day 3: 3
US-28 | 82 | Design Manual Mode conversation state and message analysis flow | Vardhan | Planning | 2- In Progress | 2 | Day 1: 2
US-28 | 83 | Implement Manual Mode analysis and multi-turn conversation continuation | Vardhan | Coding | 2- In Progress | 5 | Day 2: 5
US-28 | 84 | Test intent, sentiment, frustration, response, coaching, knowledge, and risk outputs | Vardhan | Testing | 1- To Do | 3 | Day 3: 3
US-29 | 85 | Define transcript parsing for TXT, CSV, and JSON formats | Sinjini | Planning | 2- In Progress | 2 | Day 1: 2
US-29 | 86 | Implement transcript upload, parsing, and sequential conversation replay | Sinjini | Coding | 2- In Progress | 5 | Day 2: 5
US-29 | 87 | Test uploaded transcripts and customer/agent message ordering | Sinjini | Testing | 1- To Do | 3 | Day 3: 3
US-30 | 88 | Design replay navigation and playback controls | Vardhan | Planning | 1- To Do | 2 | Day 1: 2
US-30 | 89 | Implement Next, Previous, Play/Pause, and Restart controls | Vardhan | Coding | 1- To Do | 5 | Day 2: 5
US-30 | 90 | Test sequential replay and control-state transitions | Vardhan | Testing | 1- To Do | 3 | Day 3: 3
US-31 | 91 | Define escalation-risk progression and replay summary requirements | Karthik | Planning | 1- To Do | 2 | Day 1: 2
US-31 | 92 | Integrate risk progression and overall summary after replay completion | Karthik | Coding | 1- To Do | 5 | Day 2: 5
US-31 | 93 | Test risk progression and final replay summary | Karthik | Testing | 1- To Do | 3 | Day 3: 3
US-32 | 94 | Define test cases for Manual Mode and Replay Mode deliverables | Sneha | Planning | 1- To Do | 2 | Day 1: 2
US-32 | 95 | Execute integration tests for analysis, coaching, knowledge, risk, and replay | Sneha | Testing | 1- To Do | 5 | Day 3: 5
US-32 | 96 | Document results and verify Task 7 acceptance coverage | Sneha | Documentation | 1- To Do | 3 | Day 3: 3

## Stand up Meeting
Sprint | Impediments | Action Taken
1 | Initial intent and emotion definitions and integration points needed alignment. | Finalized analysis schema, intent categories, emotion labels and integration flow.
2 | Frustration and escalation thresholds needed validation against realistic customer language. | Reviewed low, medium and high frustration examples and refined thresholds.
3 | Context inheritance and satisfaction trend needed multi-turn validation. | Added history-aware follow-up handling and tested satisfaction trends.
4 | RAG retrieval returned no results when the knowledge base was empty at startup. | Added automatic startup indexing of bundled support PDFs and verified retrieval.
5 | Final integration required regression testing across API, simulator, RAG and UI. | Ran Task 4 scenarios, API checks and end-to-end Streamlit demonstration; fixed final issues.
6 | Escalation scoring spiked prematurely on single negative keywords, and real-time coaching generation added latency to response rendering. | Introduced rolling multi-turn weighting to prevent false-positive critical alerts, and parallelized the Coaching Agent evaluation with RAG retrieval via asynchronous worker routines.
7 | Three-panel UI, Manual Mode, and Replay Mode needed coordinated integration across analysis, coaching, RAG, and escalation components. | Defined Task 7 console flow, separated Manual/Replay responsibilities, and planned message-by-message integration and testing.

## Retrospection
SL # | Sprint # | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | Sinjini, Sneha,Krishna,Vardhan, Harshitha | Define clear acceptance criteria before coding each analysis component. | Starting implementation before finalizing classification rules. | Frequent local testing after each small module. | Created a common analysis schema and tested intent/sentiment modules incrementally.
2 | 2 | Sinjini, Sneha,Krishna,Vardhan, Harshitha | Use realistic customer language to tune frustration and escalation rules. | Treating frustration and escalation independently from conversation history. | Peer review of scoring examples and edge cases. | Added repeated-complaint and escalation indicators to the scoring workflow.
3 | 3 | Sinjini, Sneha,Krishna,Vardhan, Harshitha | Add more multi-turn context scenarios. | Analyzing every message without considering previous turns. | Regression testing after each context change. | Implemented follow-up intent inheritance and satisfaction trend tracking.
4 | 4 | Sinjini, Sneha,Krishna,Vardhan, Harshitha | Validate the complete RAG pipeline from startup to response generation. | Assuming the vector database is populated without a startup check. | Testing with actual bundled support PDFs. | Added automatic knowledge-base initialization and verified grounded retrieval.
5 | 5 | Sinjini, Sneha,Krishna,Vardhan, Harshitha | Maintain end-to-end regression tests and demo readiness. | Leaving integration checks until the end of development. | Automated scenario testing and documentation review. | Completed 20+ scenario coverage, API checks, multi-turn demo and technical documentation.
6 | 6 | Sinjini, Sneha,Krishna,Vardhan, Harshitha | Asynchronous execution for real-time coaching evaluation to keep agent responses low-latency. | Evaluating tone and sentiment without accounting for prior customer turns. | Rigorous edge-case testing with aggressive customer queries. | Deployed a multi-stage scoring pipeline and tested 25+ complex escalations across support tiers.
7 | 7 | Sinjini, Sneha,Krishna,Vardhan, Harshitha,Karthik | Add automated replay tests and validate each live analysis update before final integration. | Building Manual and Replay flows independently without checking shared conversation state. | Frequent end-to-end checks across analysis, coaching, RAG, and escalation modules. | Planned a shared conversation state and message-by-message validation for both modes.

## Task 7 Architecture
TASK 7 – LIVE SUPPORT CONSOLE ARCHITECTURE
High-level architecture based on Task 7 requirements
Layer / Component | Main Responsibility | Inputs | Processing / Flow | Outputs | Task 7 Coverage
Live Support Console UI | Three-panel agent interface | Customer/agent messages; mode selection | Maintains chronological conversation view and controls | Conversation window, coaching feed, knowledge panel | Three-panel UI
Conversation Analysis | Analyze each customer message and conversation context | Customer message + conversation state | Determine intent, sentiment and frustration level | Intent, sentiment, frustration level | Manual + Replay analysis
Real-Time Coaching Engine | Generate coaching and suggested responses | Customer message + analysis/context | Produce response suggestion and coaching tips | Suggested response; tone, empathy, clarity, professionalism tips | Real-time coaching
Knowledge Recommendation Layer | Find relevant support knowledge | Current message + conversation context | Retrieve relevant FAQs, articles, policies and troubleshooting steps | Recommended knowledge content | Knowledge recommendation panel
Escalation-Risk Monitor | Track escalation risk during conversation | Message analysis + conversation progression | Evaluate and update escalation-risk state after exchanges | Risk warning and progression | Escalation-risk display
Conversation State Manager | Maintain complete session/replay state | Messages, analyses, coaching, recommendations | Store/order conversation events and current position | Current conversation/replay state | Manual state + replay controls
Manual Mode | Support live/manual simulation | Agent-entered or pasted customer message; next response | Run analysis → coaching → knowledge → risk for each exchange | Updated conversation state and feedback | Manual Mode
Replay Processor | Analyze previously recorded conversations | TXT / CSV / JSON transcript | Parse messages, display sequentially, process each customer message | Replay-ready message stream + per-message analysis | Replay Mode
Replay Controls & Summary | Control playback and summarize replay | Parsed transcript + replay state | Next/Previous, Play/Pause, Restart; summarize after completion | Replay progression + overall summary | Replay controls and summary
Agent Interaction Flow | Connect all components | Customer message / transcript event | Analysis feeds coaching, knowledge and risk; results return to UI | Agent decisions and continued conversation | End-to-end flow
End-to-End Flow
1. Input | Manual customer message OR uploaded transcript
2. Parse / State | Create or update chronological conversation state
3. Analyze | Intent + sentiment + frustration
4. Generate | Suggested response + coaching feedback
5. Recommend | FAQs + articles + policies + troubleshooting
6. Monitor | Escalation-risk warning/progression
7. Display | Update three-panel console after each exchange
8. Complete | Replay summary / continue Manual conversation

## Task 6 Architecture
TASK – 6: Coaching, Response Suggestion & Escalation Risk Architecture
Layer / Component | Input | Processing / Responsibility | Output | Connects To | Purpose
User / Conversation Input | Customer message + conversation context | Capture and maintain the current support conversation | Current customer message + context | Intent & Sentiment Analysis | Starting point for real-time analysis
Intent & Sentiment Analysis | Customer message + context | Detect customer intent, sentiment and relevant conversation signals | Intent + sentiment + analysis signals | Coaching Engine; Knowledge Recommendation; Escalation Risk | Provides context for downstream agents
Knowledge Recommendation Agent | Intent + customer message + context | Retrieve and rank relevant FAQs, support articles, policies and troubleshooting content | Top relevant knowledge recommendations | Response Suggestion; Coaching Engine | Grounds the agent response in support knowledge
Response Suggestion Engine | Customer message + intent/sentiment + knowledge | Generate a suitable suggested agent response | Suggested response | Coaching Engine; Support Agent | Helps the agent respond consistently
Coaching Engine | Suggested response + conversation signals | Evaluate tone, empathy, clarity and professionalism | Coaching feedback / improvement tips | Support Agent | Provides actionable coaching
Escalation Risk Monitor | Intent + sentiment + conversation signals | Assess escalation indicators and update risk level | Escalation-risk status / warning | Support Agent; Conversation State | Highlights conversations requiring attention
Conversation State / Integration Layer | Analysis + recommendations + coaching + risk | Combine outputs and maintain current conversation state | Unified real-time support context | Support Console / Task 7 Live Support Console | Feeds all Task 7 real-time panels
Support Agent | Unified support context | Review recommendation, coaching and risk; enter final response | Agent response | Conversation State / next exchange | Human-in-the-loop decision and response
TASK 6 END-TO-END FLOW
1 | Customer Message | Message enters the system with conversation context.
2 | Intent & Sentiment | Analyze intent, sentiment and conversation signals.
3 | Knowledge Retrieval | Find relevant FAQs, articles, policies and troubleshooting steps.
4 | Response Suggestion | Generate a suggested response using analysis + knowledge.
5 | Coaching | Evaluate tone, empathy, clarity and professionalism.
6 | Escalation Risk | Update escalation risk and produce warning when required.
7 | Agent Review | Agent reviews outputs and sends the final response.
8 | Next Exchange | Conversation state is updated and the cycle repeats.
ARCHITECTURE VIEW
CUSTOMER MESSAGE / CONVERSATION CONTEXT
↓
INTENT + SENTIMENT ANALYSIS
↓ |  | ↘ |  | ↙
KNOWLEDGE RECOMMENDATION | → | RESPONSE SUGGESTION | → | COACHING ENGINE
|  | ↓ |  | ↓
ESCALATION RISK MONITOR
↓
AGENT REVIEW / FINAL RESPONSE